## WBS - Work Plan
TASK | Start Date | End Date | Workdays | Responsibility | Deliverable | Comments
Assignment of the project | 2017-10-25 | 2017-10-25 | 1 | Team
Research of Client Organisation | 2017-10-26 | 2017-11-05 | 9 | Team
Conduct Intial Meeting | 2017-11-06 | 2017-11-06 | 1 | Team
Underatanding client needs | 2017-11-02 | 2017-11-07 | 5 | Team
Draft Project Plan, Draft Statement of Work | 2017-11-07 | 2017-11-08 | 2 | Team
finalizing Project Plan and Statement of Work | 2017-11-29 | 2017-12-06 | 8 | Team
Client current situation and major issues | 2017-11-08 | 2017-11-14 | 6 | Team
Project Definition Presentation | 2017-11-13 | 2017-11-15 | 3 | Team
Approach for the marketing and sales cycle of different buckets of clinets associated with Listing2Leasing | 2017-11-08 | 2017-11-20 | 18 | Team
Preliminary findings about improving Risk Mitigation, | 2017-11-08 | 2017-11-22 |  | Team
Preliminary findings on how to make the agents/ brokerages more profitable, | 2017-11-08 | 2017-11-24 |  | Team
Preliminary findings on how offices can be profitable from the transaction in the business | 2017-11-08 | 2017-11-26 |  | Team
Finalizing findings and recommendations | 2017-11-27 | 2017-12-04 | 7 | Team
finalizing marketing and sales cycle | 2017-11-27 | 2017-12-04 |  | Team
Review with Client | 2017-11-29 | 2017-12-06 | 7 | Team
Draft presentation and report | 2017-12-06 | 2017-12-09 | 3 | Team
Review findings, recommendations, implementation plan with client | 2017-12-09 | 2017-12-12 | 3 | Team
Presentation and Final Report | 2017-12-09 | 2017-12-13 | 4 | Team

## Gantt Chart
|  | 2017-10-25 | [6 empty] | 2017-11-01 | [6 empty] | 2017-11-08 | [6 empty] | 2017-11-15 | [6 empty] | 2017-11-22 | [6 empty] | 2017-11-29 | [6 empty] | 2017-12-06 | [6 empty] | 2017-12-13
TASK | % Compl. | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S
Assignment of the project | 100
Research of Client Organisation | 100
Conduct Intial Meeting | 100
Underatanding client needs | 100
Finalizing Project Plan and Statement of Work | 100
Client current situation and major issues | 100
Project Definition Presentation
Approach for the marketing and sales cycle of different buckets of clinets associated with Listing2Leasing | 100
Preliminary findings about improving Risk Mitigation, | 100
Preliminary findings on how to make the agents/ brokerages more profitable, | 100
Preliminary findings on how offices can be profitable from the transaction in the business | 100
Finalizing findings and recommendations
finalizing marketing and sales cycle
Review with Client
Draft presentation and report
Review findings, recommendations, implementation plan with client
Presentation and Final Report